## All
Section Heading | Action | Specific | Measurable | Appropriate | Timeline | Staff Responsible | Outcome April 2023
Strategy | Develop The Students' Union Strategic plan 2022-2026, with Sustainability as a key theme, linking to UWE Bristol 2030 core commitments. | Creation of a five year Students' Union strategy and sustainability vision, driven by student feedback from sustainability survey, NUS Skills survey data and focus groups (ensuring diversity of student input). Understand the attitudes of students and their demands of their Students' Union for the five year strategy ahead, resource this work effectively and create action plan for this time span, developed with students. Embed three questions into the survey. | Responses to the focused sustainability questions in the student survey. Strategic plan has been passed by Board of Trustees with clear sustainability content and commitments. |  | Launch to managers of the strategy house model December 2022, all staff engagement February 2023m phase 1 work for 18 months. | Tim Benford (CEO), with support from Rachel Colley (Community Manager) | Underway.
Student Engagement | Progress ethical fashion projects and roll out additional swap shop schemes for all campus sites. | 1. Creation of a new Placement Uniform Swap Shop at Glenside for Health Care students 2. Monitor uptake in first year of creation 3. Run regular up the Swap Shop events at Frenchay and Bower Ashton 4. Run regular event programmes e.g. Charity Shop Crawl, mending events 5. Focus on ethical fashion and social justice issues as part of fashion supply chains through giveaways, blogs and social media polls | Attendance at activities, use of Uniform Swap Shop, website hits for information, social media engagement statistics |  | September 2022-June 2023 | Community: Student Sustainability Engagement Coordinator and Campus Community Coordinators | Completed. https://www.thestudentsunion.co.uk/community/green-team/ourprojects/sustainable-fashion/ - https://www.thestudentsunion.co.uk/union/campuses/glenside/uniformswapshop/
Student Engagement | Improve students' understanding of energy saving techniques, especially in private rented accommodation. | 1. Creation of a project proposal with The Advice Centre, Green Team and Student Life. 2. Run a campaign week (February or March) to engage students and evaluate impact 3. Update messaging for students in private rented accommodation and disseminate 4. Embed for future plans with Student Life | Entries in competitions from the students. View stats on news articles and social media posts. |  | Planning meetings November 2022, delivery January - March 2023. | Representation: Advice Services Manager. Community: Community Projects Coordinator, Student Sustainability Coordinator | Achieved through Accommodation Fair and partnership with Student Life.
Student Engagement | To support the 2021/2022 student Sustainability Committee to lead a sustainability campaign. | 1) Regular meetings to be supported by staff 2) Campaigns training to be delivered by SOS-UK / relevant staff. 3) One key campaign run and evaluated - this year on food. The Food campaign will link to our working group (chaired by Commercial Services Director) using the NUS/SOS-UK Sustainable Food Guide and VP Community and Welfare's Healthy Eating campaign. 4) AGM in May 6) Committee members supported to run a series of smaller 'one-off' events | Survey of committee end of year to see knowledge and skills development 1. Committee meetings held once per fortnight (an increase from one per month) 2. Committee campaigns launched – (Impact assessment will be delivered) 3. Committee events run – (Impact assessment will be delivered for each one) 4. Run a successful AGM with a handover in the spring term 7. Create a series of committee social media posts/videos/articles to promote work to other students (monitor number of hits) |  | October 2022: committee recruited and in post, and successful training package delivered. January 2023: Headline campaign theme decided, market research survey to identify key focus areas and creation of campaign plan. Feb 2023: additional campaigns training by SOS-UK if the students would like / if the Student Sustainability Engagement Coordinator thinks they need it. March 2023: Campaign Events week April 2023: Evaluate campaign May 2023 - August 2023: they can continue running sustainability projects or campaigns if they would like to but some may not stay throughout the summer. | President: Sustainability Officer and Sustainability Committee Community: Student Sustainability Engagement Coordinator | Completed, March 2023.
Student Engagement | Review the events process to ensure it includes accessibility and inclusion information. | Review the current process and include information on autism awareness, other neuro-diverse inclusion information and standard event templates for the website for event leads to follow. This process will be co-created with students, especially Disabled Students Officer. | Updated process is distributed to event leads. |  | February 2023 | President: Students' Union President Community: Community Manager Buildings: Buildings Manager | Buildingd Manager Update Jan 23 - Building Staff member SarahHarnahan attended a autism course whereby she put together a template for event on our website to include more information to make it more inclusive. This has been communicated to staff and added to our How to add events on our website that is currently held by Marketing. DP next steps to review and rewrite our events process. (Timeline Oct 2023)
Student Engagement | Increase the number of clubs and societies engaged with Greener Futures Programme by 20%. Improve the support for students to engage. | 1. Review of 2021-2022 uptake 2. Rework criteria and submission process based on feedback. 3. Launch of Greener Futures Programme 2022-2023 with SU Opportunities and Presidents. 4. Support groups signed up to complete their workbook with workshops. 5. Run Mid-Year Competition to improve engagement throughout the year 6. Greener Futures Awards presented at Sports and Societies Awards May 2023 | Monitored through uptake and submissions via the Green Team, liaising with relevant elected officers to push the promotion of this. Stats from engagement with new e-learning package. |  | Review January 2023 for additional push for sign ups and completion of tasks. | Community: Student Sustainability Engagement Coordinator Opportunities: Societies Development Coordinator Presidents: VP Sport & Health and VP Socs & Comms | Completed - 38 groups, 100% increase in uptake: https://www.thestudentsunion.co.uk/community/green-team/ourprojects/greenerfutures/
Student Engagement | Increase engagement with the sustainable period product trials by 20% on 2021/2022. | • Continue relationship with WUKA to provide products at cost-price and gain budgetary support for this project. Sustainable period products: student trial project, breaking down barriers for accessing products • Run period product workshops with environmental ambassador • Run weekly stalls across the campus sites to offer free plastic free single use products and to sign up to reusable trial • Working group across the Students' Union and University to increase free period products in more toilets across the 3 sites | • Improving students’ knowledge about the full range of period products available • Increase the number of students choosing/considering sustainable period products • Improve student diversity and representation within the period conversation • Increase availability of free period products across the campus sites |  | Weekly sessions from October-December 2022, monthly in 2023 until Easter. | Community: Community Projects Coordinator | https://www.thestudentsunion.co.uk/community/green-team/ourprojects/sustainableperiodproducts/ - achieved, with over 100 students participating. More toilets stocked with natracare options across 5 sites.
Student Engagement | Drive forward new drugs harm reduction work, building on alcohol social norms as part of Drugs and Alcohol Accreditation, supporting inclusive campus culture agenda. | 1. Produce a harm reduction campaign with Bristol City Council as part of their Bristol BID Nights work 2. Promote the city-wide Bristol Rules Campaign and create an anti-spiking messaging campaign that compliments 3. Organise and run Drink Rethink, peer to peer alcohol awareness intervention 4. Analyse the annual drugs and alcohol survey data to understand student behaviour and create targeted interventions based on this 5. Work with DHI at key events of the year to promote Drugs and Alcohol harm reduction approaches | 1 & 2 - Website hit rate and social media engagement 3. Number of students engaged, feedback survey 4. Number of survey respondents 5. Number of students engaged via the stalls |  | Year round campaign, September - June | Community: Community Manager and Community Projects Coordinator Presidents: VP Com and Welfare | https://www.youtube.com/watch?v=jCTTmEzOljY&t=1s - https://www.thestudentsunion.co.uk/community/late-night-do-it-right/harmreductionalcohol/
Student Engagement | Run and engaging Speak Up week, with the aim of raising awareness of students and staff experiences of harassment, sexual assault and all forms of discrimination – particularly for those from disadvantaged and underrepresented backgrounds – and taking action as appropriate. | Launch the pledge for students and co-sign with the UWE Directorate. | Website hits, number of pledges, number of views on social media posts, signed declation with UWE Bristol. |  | October 2022. | SU President, Rania and VP Community and Welfare, Rahul. | Completed: https://www.thestudentsunion.co.uk/representation/campaigns/speak-up-week/. he President filmed a video ntroducing the campaign, which reached 4,123 views on Instagram: https://www.youtube.com/shorts/Ezi2-LrkGpQ. https://www.thestudentsunion.co.uk/news/article/thesuatuwe/UWE-Bristol-and-The-Students-Union-Sign-Speak-Up-Pledge/
Student Engagement | Achieve re-accreditation for Responsible Futures | • Support students in lobbying UWE for a mandatory climate education module, through meeting with the Vice-Chancellor and escalating their petition • Focus efforts through a targeted task and finish group to ensure this happens ready for Welcome 2023 • Run a host partnership workshop on creating authentic partnerships • Work with the UWE Careers Service and Sustainability Board to progress the fossil free careers campaign and agree to our commitments | Reaccreditation certification |  | September - May | Community: Community Manager, Student Sustainability Engagement Coordinator, Representation Team, VP Education, SU President | Reaccreditation audit in May 2023
Responsible Consumption | Understand and utilise our new energy data panel from UWE Energy, reduce 1 utility by 5% over 12 months. | 1. Work with UWE Sustainability ISO14001 to redraft this project 2. Run departmental workshops to capture negative impact and opportunities (aspects register), understand what's measurable, what's not 3. Identify key themes of work to improve reporting and create sub projects to address and then reduce impact, as relevant 4. Improve reporting tool from UWE sustainability team re year on year stats e.g. utilities, waste | UWE Energy Dashboard |  | January 2023-January 2024 | Buildings: Donna Prince Commercial: Paul Dingley | Hand over of new system November 2022. Internal meeting to discuss priority data areas January 2023. Action plan for next 12 months for February 2023.
Responsible Consumption | Increase use of zero waste outlets in Commercial Services by 5%. | 1. Run an awareness campaign on the zero waste shop in January 2023. 2. Offer giveaways and discounts as part of the SU Cost of Living Package to students and staff 3. Monitor the uptake after the initial campaign to track if it coverts to repeat usage | EPOS Data, use of discount vouchers |  | January - March 223 | Commercial: Paul Dingley Finance: Michael Blades | Completed Zero waste launched at Bower Ashton campus on 31st January 2023 as part of Bower Fair. 500 reusable bags given out and 500 x 50% discount vouchers. At Frenchay, 500 reusable bags given out and 500 x 50% discount vouchers in February, with another 500 to hand out in March. So far, this has not converted to a significant increase in usage.
Responsible Consumption | Increase purchasing and sale of Fairtrade products across commercial areas by 5% on previous academic year | 1. Review current offer in commercial areas, purchasing and sales, and identify areas to improve promotion or increase the range of Fairtrade products 2. Review products from NUS and engage the Sustainability Committee in product selection as needed 3. Work with Marketing on Fairtrade Fortnight campaigns and year-round promotion 4. Work with Marketing to display items in The Shop in the most attractive and informative way 5. Evaluate the impact of these interventions and contribute to University Fairtrade Award | Fairtrade product sales value 2018/19 v 2019/2020 v 2021/2022 v 2022-2023 (adjust for covid) |  | March 2023 run report | Commercial: Paul Dingley Finance: Michael Blades | Completed and added to Fairtrade outcomes
Responsible Consumption | Reduce single use coffe cup use from 55% of sales to 25% of sales at Frenchay campus through involvement in a 6-month reusable cup pilot scheme with City To Sea | 1. Work with UWE Hospitality and marketing colleagues to launch pilot scheme in May 2023 (trader app and testing) 2. Customer launch in June 2023. Free, no-deposit cup scheme designed to remove barrier to non-single use takeaway options 3. Monitor take up of scheme, and trial different approaches to promotion 4. Evaluate impact at end of pilot, comparing against data from 2022/23 5. Decide on long term viability | Measure percentage of single use cups vs. reusable cups used during the six month pilot. Compare against the same period last year (55% single use, 45% reusable) |  | May to October 2023 | Commercial: Paul Dingley | Along with two UWE Hospitality outlets on Frenchay campus, we have signed up Union 2 to be part of the scheme.
Responsible Consumption | Review our banking and ethical investment policy position and look at ethical banking investments for future consideration. | This will require sign-off from the Board and next board meeting is in March. Our FInance Manager will investigate potential banks, and two students from the Sustainability Committee with an educational background in finance and investment are interested to be part of this. | Ethical Investment Policy Draft approved by the Board of Trustees |  | 2023-03-01 | SU President, Rania | June board meeting
Responsible Consumption | The union has a reviewed its purchasing policy and created a checklist for managers to aid effective purchasing, contributing to a reduction in carbon footprint in this area. | 1. Internal meeting to review the current processes in place on purchasing, including amazon (marketing, commercial, engagement) in regards to sourcing and single-use plastic, ethical supply chains 2. Create a position statement and checklist for managers 3. Communicate the policy and related guides to all staff and student groups reduce where appropriate freebies in favour of environmentally friendly alternatives. Work with Sustainability Committee to create student led content re consumption, esp. around Christmas | Managers checklist rolled out. Credit card information/Log of spend with suppliers. |  | Develop December 2022, roll out after F&GP February 2023. Improve training and support for managers March 2023. | Finance: Michael Blades (all dept managers) | To be taken into new strategic planning workshops, summer 2023
Staff Culture | Roll our additional sustainability e-learning opportunities for Students' Union staff | Adopt a new e-learning platform and market to staff. Roll out mandatory caron literacy e-module to all SU Staff. Bring in new carbon footprint People HR thanks badge for staff who engage with training and create their own action plan for reducing their carbon footprint. Launch additional EDI modules as part of this social and climate justice training package. | Take up of e-learning. Submissions to the new People HR badge. |  | Mandatory carbon literacy roll out February 2023. | HR Manager and Community Manager | Carbon Literacy Badge in place. Staff who provide Carbon action plans automatically earn 50 points towards our twice yearly behaviours and values awards. This initiative is gaining momentum each year. 50% uptake against last year.
Staff Culture | Improve staff awareness of sustainability and organisation sustainability goals through continuous review of new starter process and inductions. | Creation of a new sustainability induction video for all new starters to watch. Review sustainability induction session to reflect new strategy vision. | Video produced and used in new starter induction, watch rates. |  | May 2023 completion | HR & Recruitment Co-ordinator Community Support | Completed and being utilised by new starters - Mandatory for new starters. 100% KPI
Staff Culture and student engagement | Provide Cost of Living initiatives to mitigate the cost of living impact for Students' Union staff and students. | Idnetify COL Initiatives, Implement breakfast, luch offerring, highlight our hardship policy for staff. For students: https://www.thestudentsunion.co.uk/representation/campaigns/cost-of-living-support/ | Initiatves introduced and ongoing |  | Ongoing, Review End Jan 2023 and again Easter 2023. | HR Manager and CEO | Cost of living/Harship Funds in place since 2022. 8% of employees are being supported with hardship actions. Cost of living - It is difficult to quantify due to COL being rolled into student funding. I estimate that we are spending in excess of £32k per year on COL staff support. Together with our wellbeing support we are spending £900.00 per person.
Staff Culture | Implement Real Living Wage for staff at The Students' Union | All colleageues receiving at least RLW | Reviewing Impact - Proposed implementation Aug 23 |  | 2023-08-01 | HR Manager | Implementation complete and agreement reached with all stakeholders. Implementation in August 23 - Direct cost 70K