## All
Section Heading | Action | Specific | Measurable | Appropriate | Timeline | Staff Responsible | Updates and Outcome April 2024
Strategy | Develop The Students' Union Strategic plan 2022-2026, with Sustainability as a key strategic goal and within the values set. | Creation of a five year Students' Union strategy and sustainability vision, driven by student feedback from sustainability survey, NUS Skills survey data and focus groups (ensuring diversity of student input). Understand the attitudes of students and their demands of their Students' Union for the five year strategy ahead, resource this work effectively and create action plan for this time span, developed with students. Embed three questions into the survey. | Responses to the focused sustainability questions in the student survey. Strategic plan has been passed by Board of Trustees with clear sustainability content and commitments. |  | Launched 1 August 2023, running workshops throughout 23-24. | CEO, with support from the Director of Engagement | Underway.
Student Engagement | Launch new climate education module in partnership with UWE Bristol | 1. Work with UWE Bristol on acquiring speaker 2. Draft questions and moderate event 3. Write up timely blog post with key learnings from launch event 4. Support sign ups to the new module through social media competitions and communications 5. Evaluate with UWE during the academic year | Number of students attending online launch event and number of sign ups and completion rate of the module. |  | Launch event September 2023. | Community: Student Sustainability Engagement Coordinator and Community People Leader | https://www.thestudentsunion.co.uk/news/article/thesuatuwe/Climate-Education-at-UWE-Bristol-launched-through-successful-event/
Student Engagement | Create a new Community Corner at Bower Ashton Campus, in a similar vein to the Sustainability Hub at Frenchay. This new Community Corner will provide City Campus students with cost of living support through a community larder, free hot drinks, free sustainable period products, clothing and book swap. | 1. Apply for Funding to turn the previous Students' Union shop space into a new sustainability area 2. Cost up and purchase the storage and infrastructure 3. Create the risk assessment to manage this space 4. Launch in January 2024 with our City Campus Officer 5. Evaluate impact with student feedback | Attendance at activities, use of Swap Shop, website hits for information, social media engagement statistics, number of hot drinks made, usage of the community larder. |  | October 2023 - February 2024 | Community: Student Sustainability Engagement Coordinator and Campus Community Coordinator | Launch on track for January 2024.
Student Engagement | Improve delivery of the student bike loan scheme | 1. Run an event in Welcome 2023 promoting the scheme and dispensing the bikes in one go 2. Provide students with the bike in first two weeks of term (65 bikes) 3. VP Community and Welfare to approach UWE for additional financial and storage support to add more bikes to the scheme 4. Evaluate the scheme with a student feedback survey | Number of bikes loaned, number of students on the waiting list. |  | Launch event September 2023, feedback survey March 2024, evaluation April 2024. | Commercial Services Team Leader | Launch event a success with 65 bikes dispensed
Student Engagement | To support the 2023/2024 student Sustainability Committee to lead a sustainability campaign on GreenSpaces | 1) Regular meetings to be supported by staff 2) Campaigns training to be delivered by SOS-UK / relevant staff. 3) One key campaign run and evaluated - linked to the student idea submitted by the Sustainability Officer | Survey of committee at end of year to see knowledge and skills development 1. Committee meetings held once per week (an increase on one per fortnight) 2. Committee campaigns launched – (Impact assessment will be delivered) 3. Committee events run – (Impact assessment will be delivered for each one) 4. Run a successful AGM with a handover in the spring term 7. Create a series of committee social media posts/videos/articles to promote work to other students (monitor number of hits) |  | October 2023: committee recruited and in post, and successful training package delivered. January 2024: Headline campaign theme decided, market research survey to identify key focus areas and creation of campaign plan. March 2024: Campaign Events week April 2024: Evaluate campaign | President: Sustainability Officer and Sustainability Committee Community: Student Sustainability Engagement Coordinator | Planned for March 2024, key idea decided for the campaign.
Student Engagement | Increase engagement with the sustainable period product trials by 20% on 2022-2023 and add an additional 10 toilet locations to the period poverty access scheme. | 1. Gain budgetary support for this project from UWE Bristol through cost of living funding 2. Continue relationship with WUKA to provide products at cost-price for the sustainable period product trial project, breaking down barriers for accessing sustainable products 3. Add in additional products into this trial to make it inclusive for more students 4. Create a myth busting video on periods and promote to students 5. Run weekly stalls across the campus sites to offer free plastic free single use products and to sign up to reusable trial 6. Working group across The Students' Union and University to increase free period products in more toilets across the 5 sites – deepening relationship with the University and Cleaning Services 7. Work with UWE Healthy University Group Team to support evaluation of this project | • Increase the number of students choosing/considering sustainable period products – number of participants in the trial • Increase availability of free period products across the campus sites – number of sites and number of boxes of product purchased and distributed • View rate on the social media videos and webpages |  | Weekly sessions from October-December 2023, review in January 2024 and continue until May 2024. | Community: Community Projects Coordinator | https://www.thestudentsunion.co.uk/getinvolved/thegreenteam/getinvolved/sustainableperiodproducts/ - matched sign up rate for 22/23 in first term (Dec 2023).
Student Engagement | Achieve SOS-UK Drugs and Alcohol Accreditation: drive forward drugs harm reduction communication campaign and conduct research on inclusive events. | 1. Produce a harm reduction campaign with UWE Bristol, rebranding this project and key harm reduction information 2. Promote the new UWE Bristol Drugs Specialist support service and run regular Drugs and Alcohol awareness pop ups 3. Organise and run Drink Rethink, peer to peer alcohol awareness intervention with UWE Bristol Student Life, increasing engagement 4. Analyse the annual drugs and alcohol survey data to understand student behaviour and create targeted interventions based on this 5. Co-create the redrafted UWE Drugs and Alcohol Policy, ensuring it is accessible to UWE students | 1 & 2 - Website hit rate and social media engagement 3. Number of students engaged, feedback survey 4. Number of survey respondents 5. Signed off in May by Academic Board |  | Year round campaign, September - June. Accreditation due May 2024. | Community: Community Manager and Community Projects Coordinator Presidents: VP Com and Welfare | https://www.thestudentsunion.co.uk/support/drugsincludingalcohol/ - https://blogs.uwe.ac.uk/welcome/2023/12/15/do-you-know-what-harm-reduction-means/
Responsible Consumption | Improve our scope 1, 2 and 3 carbon mapping and measuring with the support of UWE Bristol (adding new elements to measure into annual report) | 1. Work with UWE Sustainability and Carbon Team to redraft this project 2. Improve reporting tool with UWE sustainability team re year on year stats e.g. utilities, waste 3. Run a staff travel survey to gain insight into the carbon footprint - continue Plastics Pacts audit and work with UWE to turn into carbon equivalent. 4. Look at utilities usage and identify any solutions with the Carbon Team to reduce utilities | UWE Energy Dashboard - additional data collection on an annual basis of carbon impact |  | February 2024 - April 2024 | Buildings Manager | Meeting with UWE Carbon in November 2023 to scope out additional data we can review and implement. Dashboard to be reviewed in February with new suggestions costed to reduce energy wastage
Responsible Consumption | Reaccreditation of the Fairtrade University Award. | 1. Host a UWE and The Students' Union review meeting on Fair trade and The Students' Union internally review current offer in commercial areas, purchasing and sales, and identify areas to improve promotion or increase the range of Fairtrade products 2. Review products from NUSSL and engage the Sustainability Committee in product selection as needed 3. Work with Marketing on Fairtrade Fortnight campaigns and year-round promotion and to display items in The Shop in the most attractive and informative way 4. Student Sustainability Engagement Coordinator and UWE Bristol Sustainability Team to collaborate on events, communications and campaigns 5. Evaluate the impact of these interventions and contribute to University Fairtrade Award - leading to successful reaccreditation of the award | Award accreditation. Fairtrade product sales value 2018/19 v 2019/2020 v 2021/2022 v 2022-2023 v 2023-2024(adjust for covid) |  | March/April Fairtrade audit. March 2024 run EPOS/Finance report. | Commercial Services Director Finance Manager Community: Student Sustainability Engagement Coordinator | In progress and added to Fairtrade outcomes
Staff Culture | Improve staff awareness of sustainability and organisation sustainability goals through continuous review of new starter process and inductions. | 1. Review sustainability induction for new staff and Presidents and improve content 2. Deliver to 15 new starters in August 2023 and ensure all complete online e-module on 'carbon and me' 3. Conduct feedback survey on overall induction period and take findings into 'induction and training' review | Attendance at training, impact quote written, online training completion rates, feedback on induction via survey. Reward sustainability value through 'badges' on Staff Savvy (HR System) |  | 1 September 2023 | HR & Recruitment Co-ordinator Community Support | Completed and being utilised by new starters - Mandatory for new starters. All new starters attended in person training and online module.
Staff Culture | Implement new monthly staff pulse surveys on stragey. | Monthly surveys on the new strategic plan to all SU staff, including a question on sustainability. Will test understanding of organisational sustainability, training and connection to job role and objectives. | Survey Responses, qualitative and quanitivate feedback. |  | Monthly - on going | HR & Recruitment Co-ordinator Community Support | Completed, first three month data sent to Community Manager for review in management meeting.
Staff Culture and student engagement | Provide Cost of Living initiatives to mitigate the cost of living impact for The Students' Union staff and students. | Review COL support package for staff and students. Continue activity with good feedback and uptake. https://www.thestudentsunion.co.uk/representation/campaigns/cost-of-living-support/ | Initiatives introduced and ongoing |  | Ongoing | HR Manager and CEO | Cost of living/Hardship Funds in place since 2022. 8% of employees are being supported with hardship actions.
Staff Culture | Implement increase in Real Living Wage for staff at The Students' Union | All colleagues receiving at least RLW | Reviewing Impact - completed implementation of phase 1 August 23, April 1st 2024 increase to be implemented. |  | April 2024 | HR Manager | Implementation complete and agreement reached with all stakeholders.