## All
Section Heading | Action | Specific | Measurable | Appropriate | Timeline | Staff Responsible | Outcome April 2022
Strategy | Develop five year Students' Union Strategic plan, with Sustainability as a key theme, with a timeline to curate the action plan underneath top level commitments. Link to UWE Bristol 2030 core commitments. | Creation of a five year Students' Union strategy and sustainability vision, driven by student feedback from sustainability survey, NUS Skills survey data and focus groups (ensuring diversity of student input). Understand the attitudes of students and their demands of their Students' Union for the five year strategy ahead, resource this work effectively and create action plan for this time span, developed with students. Embed three questions into the survey. | Responses to the focused sustainability questions in the student survey. Strategic plan has been passed by Board of Trustees with clear sustainability content and commitments. |  | 2022-04-01 | Tim Benford (CEO), with support from Rachel Colley (Community Manager)
Student Engagement | Creation of strand student engagement projects under responsible fashion heading. | 1. Re-set up the Swap Shop 2. Run regular event programmes e.g. Charity Shop Crawl, mending events | Attendance at activities |  | Welcome - June | Community: Student Sustainability Engagement Coordinator and VP Community and Welfare
Student Engagement | Improve students' understanding of energy saving techniques in UWE Managed Accommodation and ways to implement in private rented accommodation. | 1. Creation of a project proposal with UWE energy and UWE Accommodation, as part of Hallslife 2. Run a campaign week (February or March) to engage students in Halls and evaluate impact 3. Update messaging for students in private rented accommodation and disseminate 4. Embed for future plans with HallsLife/Campus Life activity | UWE energy stats on consumption. Entries in competitions from the students. View stats on news articles and social media posts. |  | February - March 2022 | Community: Community Projects Assistant
Student Engagement | To support the 2021/2022 student Sustainability Committee to lead a behaviour change campaign. | 1) Regular meetings to be supported by staff 2) Project management and effective campaign training to be delivered by the old committee in a handover session/social 3) One key campaign run and evaluated 4) AGM in May 6) Committee members supported to run a series of smaller 'one-off' events 7) Committee to speak at a Green Team event | Survey of committee pre and post to see knowledge and skills development 1. Committee meetings held once per fortnight (and increase from one per month) 2. Committee campaigns launched – (Impact assessment will be delivered for each one) 3. Committee events run – (Impact assessment will be delivered for each one) 4. Run a successful AGM with a handover in the spring term 7. Create a series of committee social media posts/videos/articles to promote work to other students (monitor number of hits) |  | October 2021: Successful AGM January 2022: Headline campaign theme decided, market research survey to identify key focus areas and creation of campaign plan March 2022: Campaign Events week April 2022: Evaluate campaign May 2022 Handover | President: Sustainability Officer and Sustainability Committee Community: Student Sustainability Engagement Coordinator
Student Engagement | Engage UWE Students in action for COP26 | 1. Work with Presidents to create social media content 2. Work with UWE sustainability to offer virtual COP26 themed events to support staff and students to understand COP and how to engage 3. Create a network of students going to COP26 and secure news articles | Number of views of videos and articles. Engagement in events. |  | October - November 2021 | Community: Student Sustainability Engagement Coordinator | https://www.thestudentsunion.co.uk/news/article/thesuatuwe/Student-Blog-How-you-can-get-involved-with-COP26/
Student Engagement | Increase the number of clubs and societies engaged with Greener Futures Programme by 10%. Improve the support for students to engage. | 1. Review of 2020-2021 uptake 2. Rework criteria and submission process based on feedback. 3. Launch of Greener Futures Programme 2021-2022 with SU Opportunities and Presidents. 4. Support groups signed up to complete their workbook with workshops. 5. Run Mid-Year Competition to improve engagement throughout the year, offer additional e-learning training package for students to engage with and gain points through completion and reflective activities. NEW OFFERING. 6. Greener Futures Awards presented at Sports and Societies Awards May 2022. | Monitored through uptake and submissions via the Green Team, liaising with relevant elected officers to push the promotion of this. Stats from engagement with new e-learning package. |  | Review January 2022 for additional push for sign ups and completion of tasks. | Community: Student Sustainability Engagement Coordinator Opportunities: Societies Development Coordinator Presidents: VP Sport & Health and VP Socs & Comms
Student Engagement | Progress Students' Union Period Poverty and periods and plastics campaign through student trial and awareness campaign | • Establish relationship with WUKA to provide products at cost-price and gain budgetary support for this project. Sustainable period products: student trial project, breaking down barriers for accessing products • Run period product workshops with environmental ambassador • Work with Commercial Services and Marketing Departments to create point of sale and social media marketing campaigns • Working group across the Students' Union and University to reduce/eliminate/address period poverty among UWE students - take request to HUG group | • Improving students’ knowledge about the full range of period products available • Increase the number of students choosing/considering sustainable period products • Increase sales of menstrual cups in SU shop • Improve student diversity and representation within the period conversation |  | February and March 2022 sessions | Community: Community Projects Assistant
Student Engagement | Drive forward new drugs harm reduction work, building on alcohol social norms as part of new pilot Alcohol and Drugs Accreditation, supporting inclusive campus culture agenda. | Produce a new drugs harm reduction video with UWE Bristol and release a new and updated alcohol harms reduction poster campaign, based off recent survey data. | Video is created and live, watch statistics. Posters disseminated into every flat in UWE managed accommodation. |  | Video produced for October 2021 release, Posters in Halls for new student arrival September 2021. | Community: Community Manager and Residences Community Coordinator Opportunities: Opportunities Manager Presidents: VP Sport & Health and VP Com and Welfare | https://www.youtube.com/watch?v=jCTTmEzOljY&t=1s - https://www.thestudentsunion.co.uk/community/late-night-do-it-right/harmreductionalcohol/
Responsible Consumption | Improve our reporting of The Students' Union's negative environmental impact. | 1. Work with UWE Sustainability ISO14001 to redraft this project 2. Run departmental workshops to capture negative impact and opportunities (aspects register), understand what's measurable, what's not 3. Identify key themes of work to improve reporting and create sub projects to address and then reduce impact, as relevant 4. Improve reporting tool from UWE sustainability team re year on year stats e.g. utilities, waste | UWE sustainability data, mapping outcomes and aspects register |  | December - April | Buildings: Donna Prince, all managers | Update 22/12/2021 Currently mapping all activities in Dec/Jan Then will mean to decide scope Then identifiy a min of five negative impact Then deep dive of these to produce data Then report on our website
Responsible Consumption | President set the following target as part of their Our World, Our Choice Campaign: REDUCE THE STUDENTS' UNION SINGLE PLASTICS IN OUR COMMERCIAL OUTLETS BY 50% BY THE END OF THIS ACADEMIC YEAR, ON THE WAY TO 100%. https://www.thestudentsunion.co.uk/representation/campaigns/owoc/ | 1. Creation of UWE Bristol working group on plastics, agree a timeline and action plan for addressing Plastic Pacts 2025 commitments 2. Through negative environmental impact mapping, identify key areas where single use plastic is consumed 3. With EPOS data and UWE Bristol assistance, audit plastics in outlets 4. Work with NUSSL supply chains to identify where reductions can be made and publish action plan to reach the target goal | Plastics audit data. |  | All year. | Commercial: Paul Dingley Finance: Michael Blades and Presidents.
Responsible Consumption | Increase purchasing and sale of Fairtrade products across commercial areas by 5% on previous academic year | 1. Review current offer in commercial areas, purchasing and sales, and identify areas to improve promotion or increase the range of Fairtrade products 2. Review products from NUS and engage the Sustainability Committee in product selection as needed 3. Work with Marketing on Fairtrade Fortnight campaigns and year-round promotion 4. Work with Marketing to display items in The Shop in the most attractive and informative way 5. Evaluate the impact of these interventions | Fairtrade product sales value 2018/19 v 2019/2020 v 2020/2021 v 2021/2022 |  | March 2021 run report | Commercial: Paul Dingley Finance: Michael Blades
Responsible Consumption | The union has a policy on freebies and giveaways and actively reviews its purchasing to identify inefficiencies and opportunities to reduce environmental impact. | 1. Internal meeting to review the current processes in place on giveaways (marketing, commercial, engagement) in regards to sourcing and single-use plastic 2. Improve the formal process which guides teams to utilise the credit card 3. Communicate the policy and related guides to all staff and student groups reduce where appropriate freebies in favour of environmentally friendly alternatives. Work with Sustainability Committee to create student led content re consumption | Credit card information/Log of spend with suppliers. |  | Review January 2022, Improve training and support for managers March 2022. | All Departments, with support from Finance Department | https://www.thestudentsunion.co.uk/news/article/thesuatuwe/How-to-be-an-eco-warrior-this-festive-season/
Staff Culture | Roll our additional sustainability e-learning opportunities for Students' Union staff | Adopt a new e-learning platform and market to staff. Engage Students' Union staff in feedback on the developing carbon literacy module, which will be mandatory upon roll out. Bring in new carbon footprint People HR thanks badge for staff who engage with training and create their own action plan for reducing their carbon footprint. | Take up of e-learning. Submissions to the new People HR badge. |  | January 2022 roll out | HR Manager and Community Manager
Staff Culture | Improve staff awareness of sustainability and organisation sustainability goals through continuous review of new starter process and inductions. | Creation of a new sustainability induction video for all new starters to watch. Review sustainability induction session to reflect new strategy vision. | Video produced and used in new starter induction, watch rates. |  | August 2021 completion | HR & Recruitment Co-ordinator Community Support | Completed and being utilised by new starters